## Gantt Chart
EDEN FRESH: GANTT CHART
PROJECT TITLE |  | Eden Fresh |  |  |  |  | TEAM NAME | [6 empty] | Team Web Crawlers
PROJECT TEAM LEADER |  | Justin |  |  |  |  | DATE | [6 empty] | 2022-10-27
PROJECT TEAM MEMBERS |  | Alexander, Devarsh, Kayla, Sze | [5 empty] | Justin |  |  | Alexander |  |  |  | Kayla |  |  | Devarsh |  |  |  | Sze
NUMBER | USER STORY | START DATE | DUE DATE |  |  | DURATION (Hours) | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
|  |  |  | STATUS | Progress |  | Sprint 5 |  |  |  |  | Sprint 6 |  |  |  |  | Sprint 7 |  |  |  |  | Sprint 8 |  |  |  |  | Sprint 9 |  |  |  |  | Sprint 10 |  |  |  |  | Sprint 11 |  |  |  |  | Sprint 12 |  |  |  |  | Sprint 13 |  |  |  |  | Sprint 14 |  |  |  |  | Sprint 15 |  |  |  |  | Sprint 16
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Set Up Shop | 2022-02-21 | 2022-02-26 | TO DO | 0% | 29 H
1.1 | UI/UX page (front end activity) |  |  | TO DO | 0% | 6 H | Sprint 5 M: JUSTIN
1.2 | framwork (back end activity) |  |  | TO DO | 0% | 6 H | Sprint 5 T: Alexander
1.3 | Database (storage activity) |  |  | TO DO | 0% | 6 H | Sprint 5 W: DEVARSH
1.4 | post Current products testing |  |  | TO DO | 0% | 4 H | Sprint 5 T: Sze
1.5 | delete a posted product testing |  |  | TO DO | 0% | 3 H | Sprint 5 T: Kayla
1.6 | post preferred meet up location testing |  |  | TO DO | 0% | 4 H | Sprint 5 W: JUSTIN
2 | Reservation and Transaction | 2022-02-28 | 2022-03-05 | TO DO | 0% | 36 H
2.1 | UI/UX page (front end activity) |  |  | TO DO | 0% | 5 H | Sprint 6 M: Alexander
2.2 | framwork (back end activity) |  |  | TO DO | 0% | 9 H | Sprint 6 T: Kayla
2.3 | Database (storage activity) |  |  | TO DO | 0% | 7 H | Sprint 6 T: Sze
2.4 | request, acceept and deny a product reservation testing |  |  | TO DO | 0% | 6 H | Sprint 6 T: DEVARSH
2.5 | cancel a product reservation testing |  |  | TO DO | 0% | 4 H | Sprint 6 W: JUSTIN
2.6 | view and change current state amount transaction testing |  |  | TO DO | 0% | 4 H | Sprint 6 W: Alexander
3 | Request Fulfilment | 2022-03-07 | 2022-03-12 | TO DO | 0% | 33 H
3.1 | UI/UX page (front end activity) |  |  | TO DO | 0% | 5 H | Sprint 7 M: DEVARSH
3.2 | framwork (back end activity) |  |  | TO DO | 0% | 10 H | Sprint 7 M: Sze
3.3 | Database (storage activity) |  |  | TO DO | 0% | 6 H | Sprint 7 W: Kayla
3.4 | Post, reply, & accept fulfillment bid testing |  |  | TO DO | 0% | 6 H | Sprint 7 T: JUSTIN
3.5 | View currant state of transaction testing |  |  | TO DO | 0% | 5 H | Sprint 7 W: Alexander
4 | Miles Radius Search | 2022-03-14 | 2022-03-19 | TO DO | 0% | 18 H
4.1 | UI/UX page (front end activity) |  |  | TO DO | 0% | 4 H | Sprint 8 M: DEVARSH
4.2 | framwork (back end activity) |  |  | TO DO | 0% | 6 H | Sprint 8 T: JUSTIN
4.3 | Database (storage activity) |  |  | TO DO | 0% | 4 H | Sprint 8 M: Kayla
4.4 | Input search location testing |  |  | TO DO | 0% | 2 H | Sprint 8 T: Sze
4.5 | Select miles radius search constraint testing |  |  | TO DO | 0% | 2 H | Sprint 8 W: Alexander
5 | Cuisine Filter | 2022-03-14 | 2022-03-19 | TO DO | 0% | 19 H
5.1 | UI/UX page (front end activity) |  |  | TO DO | 0% | 4 H | Sprint 8 M: DEVARSH
5.2 | framwork (back end activity) |  |  | TO DO | 0% | 6 H | Sprint 8 T: JUSTIN
5.3 | Database (storage activity) |  |  | TO DO | 0% | 4 H | Sprint 8 M: Kayla
5.4 | Select & apply predefined cuisine to filter results |  |  | TO DO | 0% | 5 H | Sprint 8 W: Sze
6 | Real Time Notifications | 2022-03-21 | 2022-03-26 | TO DO | 0% | 36 H
6.1 | UI/UX page (front end activity) |  |  | TO DO | 0% | 5 H | Sprint 9 M: Alexander
6.2 | framwork (back end activity) |  |  | TO DO | 0% | 13 H | Sprint 9 T: DEVARSH
6.3 | Database (storage activity) |  |  | TO DO | 0% | 6 H | Sprint 9 T: JUSTIN
6.4 | Receive & view Notifications testing |  |  | TO DO | 0% | 5 H | Sprint 9 T: Kayla
6.5 | Opt -in to receive & not receive notifications testing |  |  | TO DO | 0% | 5 H | Sprint 9 W: Sze
6.6 | deleting notification check |  |  | TO DO | 0% | 2 H | Sprint 9 W: Alexander
7 | Transaction View | 2022-03-21 | 2022-03-26 | TO DO | 0% | 28 H
7.1 | UI/UX page (front end activity) |  |  | TO DO | 0% | 5 H | Sprint 9 M: DEVARSH
7.2 | framwork (back end activity) |  |  | TO DO | 0% | 10 H | Sprint 9 T: JUSTIN
7.3 | Database (storage activity) |  |  | TO DO | 0% | 5 H | Sprint 9 T: Kayla
7.4 | view & Edit alll product reservations and request |  |  | TO DO | 0% | 5 H | Sprint 9 T: Sze
7.5 | Open direct chat to other party |  |  | TO DO | 0% | 3 H | Sprint 9 T: Alexander
8 | Meeting Point Directions | 2022-03-28 | 2022-04-02 | TO DO | 0% | 21 H
8.1 | UI/UX page (front end activity) |  |  | TO DO | 0% | 4 H | Sprint 10 M: DEVARSH
8.2 | framwork (back end activity) |  |  | TO DO | 0% | 7 H | Sprint 10 T: JUSTIN
8.3 | Database (storage activity) |  |  | TO DO | 0% | 4 H | Sprint 10 T: Kayla
8.4 | view street directions to the meetin location tetsing |  |  | TO DO | 0% | 3 H | Sprint 10 W: Sze
8.5 | Input origin location testing |  |  | TO DO | 0% | 2 H | Sprint 10 W: Alexander
9 | Following Sellers | 2022-04-03 | 2022-04-09 | TO DO | 0% | 30 H
9.1 | UI/UX page (front end activity) |  |  | TO DO | 0% | 6 H | Sprint 11 M: DEVARSH
9.2 | framwork (back end activity) |  |  | TO DO | 0% | 12 H | Sprint 11 M: JUSTIN
9.3 | Database (storage activity) |  |  | TO DO | 0% | 6 H | Sprint 11 T: Kayla
9.4 | Follow & unfollow sellers testing |  |  | TO DO | 0% | 4 H | Sprint 11 W: Sze
9.5 | View following testting |  |  | TO DO | 0% | 2 H | Sprint 11 W: Alexander
10 | Rating and Review | 2022-04-11 | 2022-04-16 | TO DO | 0% | 27 H
10.1 | UI/UX page (front end activity) |  |  | TO DO | 0% | 4 H | Sprint 12 M: DEVARSH
10.2 | framwork (back end activity) |  |  | TO DO | 0% | 11 H | Sprint 12 T: JUSTIN
10.3 | Database (storage activity) |  |  | TO DO | 0% | 5 H | Sprint 12 W: Kayla
10.4 | Review and rating from 1-5 star scale testing |  |  | TO DO | 0% | 5 H | Sprint 12 W: Sze
10.5 | View posted rating and reviews |  |  | TO DO | 0% | 2 H | Sprint 12 W: Alexander
11 | User Block Feature | 2022-04-11 | 2022-04-16 | TO DO | 0% | 26 H
11.1 | UI/UX page (front end activity) |  |  | TO DO | 0% | 6 H | Sprint 12 M: Alexander
11.2 | framwork (back end activity) |  |  | TO DO | 0% | 9 H | Sprint 12 T: Sze
11.3 | Database (storage activity) |  |  | TO DO | 0% | 5 H | Sprint 12 T: Kayla
11.4 | Block & unblock users testing |  |  | TO DO | 0% | 3 H | Sprint 12 W: DEVARSH
11.5 | View block list testing |  |  | TO DO | 0% | 3 H | Sprint 12 W: JUSTIN
12 | Chat Feature | 2022-04-18 | 2022-04-23 | TO DO | 0% | 25 H
12.1 | UI/UX page (front end activity) |  |  | TO DO | 0% | 4 H | Sprint 13 M: Alexander
12.2 | framwork (back end activity) |  |  | TO DO | 0% | 6 H | Sprint 13 T: Sze
12.3 | Database (storage activity) |  |  | TO DO | 0% | 4 H | Sprint 13 T: DEVARSH
12.4 | Send chat request testing |  |  | TO DO | 0% | 2 H | Sprint 13 W: JUSTIN
12.5 | accept or decline a chat request testing |  |  | TO DO | 0% | 4 H | Sprint 13 T: S; Sprint 13 W: J; Sprint 13 R: K; Sprint 13 F: D
12.6 | Communicate with users using the chat testing |  |  | TO DO | 0% | 3 H | Sprint 13 W: Kayla

## Roadmap
RoadMap
[7 empty] | Start Date: | 2022-01-24
[7 empty] | End Date: | 2022-04-23
2021 | [6 empty] | 2022
AUG | SEP | OCT |  |  | NOV | DEC | Jan |  | Feb |  |  |  | MAR | [7 empty] | APR
Start Date |  | End Date | Start Date | End Date | Start Date | End Date | Start Date | End Date | Start Date | End Date | Start Date |  | End Date | Start Date |  |  | End Date | Start Date |  |  | End Date | Start Date | End Date
2021-09-20 |  | 2021-10-06 | 2021-10-11 | 2021-10-27 | 2021-11-15 | 2021-12-01 | 2022-01-24 | 2022-01-29 | 2022-02-07 | 2022-02-12 | 2022-02-21 |  | 2022-03-12 | 2022-03-14 |  |  | 2022-03-26 | 2022-03-28 |  |  | 2022-04-16 | 2022-04-18 | 2022-04-23
Phase1: Plan/Design |  | 2021-10-11: Phase2: Analysis/Design; 2021-11-15: Phase2: Design; 2022-01-24: Phase1: Core requirement1; 2022-02-07: Phase2: Core requirement2; 2022-02-21: Phase3:Festures1 (Produce Post) |  |  | Phase4: Features2 |  |  |  | Phase5: Feeatures3 |  |  |  | Phase6: Features4
Task |  | Member | Task2 | Member | Task3 | Member | Task1 | Task2 | Task1 |  | Task1 | Task2 | Task3 | Task1 | Task2 | Task3 | Task4 | Task1 | Task2 | Task3 | Task4 | Task1
BRD |  | Justin & Kayla | Project Plan | Devarsh & Sze | Low Level design | Not assign yet | Account creation |  | Logout |  | Phase3:Festures1 (Produce Post) Task1: Set-up Shop; Phase4: Features2 Task1: Miles Radius Search; Phase5: Feeatures3 Task1: Meeting Point Directions; Phase6: Features4 Task1: Chat Feature
Technical Specifications |  | Alexander | Test Plan | Justin & Kayla | UM | Not assign yet |  | Account deletion |  |  | Phase3:Festures1 (Produce Post) Task2: Reservation and Transaction; Phase4: Features2 Task2: Cuisine Filter; Phase5: Feeatures3 Task2: Following Sellers
High Level design |  | Devarsh | Network Diagram | Alexander | Logging | Not assign yet |  |  |  |  | Phase3:Festures1 (Produce Post) Task3: Request Fulfillment; Phase4: Features2 Task3: Real-Time Notifications; Phase5: Feeatures3 Task3: Rating And Review
Sitemap |  | Sze | [8 empty] | Phase4: Features2 Task4: Transaction View; Phase5: Feeatures3 Task4: User Block Feature