## Gantt Chart
EDEN FRESH: GANTT CHART
PROJECT TITLE |  | Eden Fresh |  |  | TEAM NAME | [6 empty] | Team Web Crawlers
PROJECT TEAM LEADER |  | Justin |  |  | DATE | [6 empty] | 2022-10-27
PROJECT TEAM MEMBERS |  | Alexander, Devarsh, Kayla, Sze
NUMBER | USER STORY | START DATE | DUE DATE | DURATION (Days) | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[5 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Set Up Shop | 2022-01-24 | 2022-01-29 | 5 | bar: WEEK 1 M to WEEK 2 W
2 | Reservation and Transaction | 2022-01-31 | 2022-02-05 | 5
3 | Request Fulfilment | 2022-02-07 | 2022-02-12 | 5 | bar: WEEK 3 M to WEEK 3 F
4 | Miles Radius Search | 2022-02-14 | 2022-02-19 | 5 | bar: WEEK 4 M to WEEK 4 F
5 | Cuisine Filter | 2022-02-21 | 2022-02-26 | 5
6 | Real Time Notifications | 2022-02-28 | 2022-03-05 | 5 | bar: WEEK 6 M to WEEK 6 F
7 | Transaction View | 2022-03-07 | 2022-03-12 | 5 | bar: WEEK 7 M to WEEK 7 F
8 | Meeting Point Directions | 2022-03-14 | 2022-03-19 | 5
9 | Following Sellers | 2022-03-21 | 2022-03-26 | 5 | bar: WEEK 9 M to WEEK 9 F
10 | Rating and Review | 2022-04-04 | 2022-04-09 | 5 | bar: WEEK 10 M to WEEK 10 F
11 | User Block Feature | 2022-04-11 | 2022-04-16 | 5
12 | Chat Feature | 2022-04-18 | 2022-04-23 | 5 | bar: WEEK 12 M to WEEK 12 F